## issues (2)
# | Tracker | Parent task | Status | Priority | Subject | Assignee | Updated | Target version | Description
49 | Feature |  | Resolved | High | Persistence: Save search criteria, title, and description so that it can be retrieved and shared. | Jonathan Pund | 2015-06-22 17:21 | 0.0 Tracer Bullet | As a user, I want to be able to save my current search criteria with a title and description, so that I can share it with other people and they can use the same criteria. (e.g. "Here's a list of severe food-related enforcement activities in the DC metro area of VA, MD, DC.")
47 | Feature |  | Resolved | High | Tracer bullet, UI: Return aggregate counts based on type filter criteria | Matt Travers | 2015-06-22 17:18 | 0.0 Tracer Bullet | As a user, I want to be able to select any combination of the enforcement types (i.e. Food, Drug, device) and receive an updated visual of the map that reflects those criteria, so I can tailor the visualization to my needs.
54 | Feature |  | Resolved | Normal | Add from/to date filtering to counts endpoint | Jonathan Pund | 2015-06-22 17:16 | 0.0 Tracer Bullet
52 | Feature |  | Resolved | Normal | Add unit tests for /fda/counts/nouns endpoint | Jonathan Pund | 2015-06-22 17:16 | 0.0 Tracer Bullet
51 | Feature |  | Resolved | Normal | Add noun validation to /fda/counts/nouns call | Jonathan Pund | 2015-06-22 17:16 | 0.0 Tracer Bullet
53 | Feature |  | Resolved | Urgent | Switch /fda/counts/nouns endpoint to use local data | Jonathan Pund | 2015-06-23 09:29 | 0.1 (Mon)
65 | Feature | Feature #56: Update filtering options and include autocomplete. | Resolved | High | Create autocomplete endpoints | Jonathan Pund | 2015-06-22 17:19 | 0.1 (Mon) | 1) Product description 2) Reason for recall
66 | Feature | Feature #56: Update filtering options and include autocomplete. | Resolved | High | Update counts endpoint to incorporate new field criteria | Jonathan Pund | 2015-06-22 17:19 | 0.1 (Mon) | 1) Product Description 2) Reason for recall 3) Classification (i.e. severity) 4) Recalling firm
67 | Feature |  | Resolved | High | Create new endpoint for returning details of enforcement events | Jonathan Pund | 2015-06-24 07:51 | 0.1 (Mon) | Parameters for endpoint: Search parameters + state/nationwide + pagination + how many per page + sort order Return values for table: 1) Event ID/recall number 2) Product description 3) Date 4) Product Type (drugs, food, devices) 5) Reason for recall 6) Severity
56 | Feature |  | Resolved | High | Update filtering options and include autocomplete. | Matt Travers | 2015-06-23 07:07 | 0.1 (Mon) | As a user, I want to be able to filter results across all available enforcement fields with the most useful fields first, so that I can quickly and easily get the results that are most important to me. Tasks: 1) Implement a design that takes into account user preferences for field order. 2) For free text fields (e.g. description), allow text searches and an autocomplete. Enforcement Fields: { "reason_for_recall": "Labeling: Incorrect or Missing Lot and/or Expiration date; The Lot and/or Expiration date on the tube may not be legible in this lot..", "status": "Ongoing", "distribution_pattern": "Nationwide and Puerto Rico, and Panama.\nMilitary distribution made.", "product_quantity": "99,660 tubes", "recall_initiation_date": "2013-02-19", "state": "NE", "event_id": "64372", "product_type": "Drugs", "product_description": "Target Up & Up, athlete's foot cream, full prescription strength, terbinafine hydrochloride 1% antifungal, 30 g (1 oz), compare to active ingredient in Lamisil, NDC 0067-6382-30 & UPC code: 300676382302 (Novartis) Target NDC 1167-3401-04, Distributed by Target Corp., Minneapolis, MN.", "country": "US", "city": "Lincoln", "recalling_firm": "Novartis Consumer Health", "report_date": "2013-06-12", "voluntary_mandated": "Voluntary: Firm Initiated", "classification": "Class III", "code_info": "Lot numbers and exp dates: 10108716 31-Mar-2013, \n10111510 30-Apr-2013, 10113801 31-May-2013, 10113839 30-Apr-2013, 10115616 31-Aug-2013", "openfda": {}, "initial_firm_notification": "Letter" }
72 | Feature |  | Resolved | Normal | Convert classification on recall events and counts call to take multiple values | Jonathan Pund | 2015-06-22 17:17 | 0.1 (Mon)
68 | Feature |  | Resolved | Urgent | Provide full details of a specific event (server side) | Jonathan Pund | 2015-06-23 10:55 | 0.2 (Tues)
60 | Feature | Feature #67: Create new endpoint for returning details of enforcement events | Resolved | High | Provide table of details of event counts (and name and description, if available) | Matt Travers | 2015-06-24 07:51 | 0.2 (Tues) | As a user, I'd like to be able to see the detailed information for all the events in my current search, so that I know the specifics.
58 | Feature |  | Resolved | High | Sharing searches via email | Matt Travers | 2015-06-24 12:12 | 0.2 (Tues) | As a user, I'd like to be able to email my friends a search that I have saved with a note, so that I can share what I found with people that need to know.
57 | Feature |  | Resolved | High | Allow users to save, name, and describe search criteria | Matt Travers | 2015-06-24 07:49 | 0.2 (Tues) | As a user, I want to be able to save, name, and describe the search criteria currently input, so that I can return to it later or share it with other people.
50 | Feature |  | Resolved | High | Analysis: Review enforcement distribution field for possible normalization | Paul Malone | 2015-06-24 12:13 | 0.2 (Tues) | Core question is whether we want to try and normalize the data or rely on it "as-is" from the API.
61 | Feature |  | Resolved | High | Complete first pass of UX design for review with focus group | Scott McCaughey | 2015-06-24 10:02 | 0.2 (Tues)
75 | Feature |  | Resolved | Normal | Add new filter criteria from counts endpoint to filter save endpoint | Jonathan Pund | 2015-06-24 12:14 | 0.2 (Tues)
78 | Feature |  | Resolved | Normal | Create new endpoint for retrieving filter by ID | Jonathan Pund | 2015-06-24 12:13 | 0.2 (Tues)
59 | Feature |  | Resolved | Normal | Share a saved search via social media and short link | Matt Travers | 2015-06-24 12:12 | 0.2 (Tues) | As a user, I'd like to post a saved search on social media (e.g. Twitter, Facebook) with a short link, so that I can use my search to generate larger dialogues about the topic.
87 | Feature |  | Resolved | Normal | UI, when map has 0 results, it should default to "lowest" palette color | Matt Travers | 2015-06-24 12:25 | 0.2 (Tues) | As-is, map turns black and users thought this was unaesthetic.
86 | Feature |  | Resolved | Normal | UI, hide table on load so that "No Results" doesn't show | Scott McCaughey | 2015-06-24 12:24 | 0.2 (Tues) | FEEDBACK: Having the page start empty was initially disconcerting. Resolution was to hide the empty table on page load.
92 | Feature |  | Resolved | Normal | UI, remove keyword search in top right | Scott McCaughey | 2015-06-24 12:32 | 0.2 (Tues) | Users found the "in table" search confusing.
82 | Feature | Feature #81: UI, Multi-select: Keep selected state(s) highlighted | Resolved | High | Endpoint: Support multi-select for states | Jonathan Pund | 2015-06-24 18:01 | 0.3 (Weds) | Endpoint needs to return multiple results for multiple selections for state.
81 | Feature |  | Resolved | High | UI, Multi-select: Keep selected state(s) highlighted | Matt Travers | 2015-06-25 15:43 | 0.3 (Weds) | As a user, I want to select multiple states by clicking each of them and having them stay highlighted, so I can visually see all the state filters I've selected.
94 | Feature |  | Resolved | Normal | UI, saving: Description not required | Matt Travers | 2015-06-24 21:43 | 0.3 (Weds) | Both are currently required, but name probably needs to remain so. Will make description non-required.
85 | Feature |  | Resolved | Normal | UI, clear filter button | Matt Travers | 2015-06-25 08:02 | 0.3 (Weds) | As a user, I would like a way to clear all my filters (both left side and states), so that I can start a new search.
80 | Feature |  | Resolved | Normal | Add State column to Table | Matt Travers | 2015-06-24 14:30 | 0.3 (Weds) | FEEDBACK: No visual feedback to indicate that table updated with results of filter.
93 | Feature |  | Resolved | Normal | UI, share: Move sharing position | Scott McCaughey | 2015-06-24 13:31 | 0.3 (Weds) | o FEEDBACK: Share button should be right under the map and above the table. Maybe on the right side. Could also do it above the map, but logical place seems to be between the two.
88 | Feature |  | Resolved | Low | UI, autocomplete: Turn off autocomplete on Reason for Recall and Product Description | Matt Travers | 2015-06-24 21:44 | 0.3 (Weds) | FEEDBACK: Reason for Recall and Product Description autocomplete are not very useful. I?d rather search for the word ?Peanuts? and not select the whole phrase. The results are usually too specific and are hard to read because they?re truncated.
84 | Bug |  | Resolved | Urgent | UI, table: Allow more than 100 results | Jonathan Pund | 2015-06-25 16:58 | 0.4 (Thurs) | Currently, there's a bug that limits table results to 100.
99 | Bug |  | Resolved | Urgent | Datatables error in IE11 |  | 2015-06-25 11:33 | 0.4 (Thurs) | See attached for the warning. Steps to reproduce: 1) In IE11, unclick Devices and Drugs 2) Click on California
95 | Bug |  | Resolved | High | Filter by product type: Must reselect state for change to take effect. No way to see for entire map. | Matt Travers | 2015-06-25 15:47 | 0.4 (Thurs) | Aaron had an issue where he had to reselect state for the change to take effect.
91 | Feature | Feature #90: UI, modal pop-up for full details: Provide full event details in pop-up when clicking a row | Resolved | High | UI, hook up endpoint for full details on row click | Matt Travers | 2015-06-25 18:56 | 0.4 (Thurs) | The full details endpoint is done (68), and needs to be hooked up with Scott's work for popping it up in a modal on click.
101 | Feature |  | Resolved | High | Pop-up for full details | Matt Travers | 2015-06-25 18:55 | 0.4 (Thurs)
90 | Feature |  | Resolved | High | UI, modal pop-up for full details: Provide full event details in pop-up when clicking a row | Scott McCaughey | 2015-06-28 22:30 | 0.4 (Thurs) | As a user, I want to be able to click on a row and get the full event details for all the fields for that event, so that I can get all the information. Full details fields: o State (i.e. map for filter, first column in table if possible) o Type (i.e. Food, Device, Drug) o Product Description o Reason for Recall o Classification/Severity o Recalling firm o Recall date initiated o Status o Not needed in table or filtering, but should be left in full details: ? Voluntary ? Report Date (too confusing with recall date) ? Code info ? Initial firm notification
102 | Bug |  | Resolved | Normal | Endpoint: Don't make state required for filter | Jonathan Pund | 2015-06-25 09:59 | 0.4 (Thurs)
103 | Bug |  | Resolved | Normal | On page load don't hide results table any more | Scott McCaughey | 2015-06-26 09:34 | 0.4 (Thurs)
107 | Bug |  | Resolved | Normal | Share: Not clear that search must be saved before sharing. | Jonathan Pund | 2015-06-26 13:05 | 0.5 (Fri) | Share only works when the search is first saved. Otherwise the link does not display the sent search. It should not be necessary to save a search in order to send, but if so, either disable the share links until the search is saved or prompt the user to save upon clicking share. Possible fixes: 1) Share (if unsaved) prompts you to save search first. 2) Share disabled until search is saved. 3) Don't require search to be saved.
97 | Bug |  | Resolved | Normal | Email to friend: Link didn't return search results. | Jonathan Pund | 2015-06-29 12:23 | 0.5 (Fri) | Link did not direct to search results. Map sizing is also off when accessed via permalink (using Chrome). Email body expecting vairables (see "Additional Bugs")
106 | Bug |  | Resolved | Normal | States do not wrap and require horizontal scrolling | Matt Travers | 2015-06-29 12:24 | 0.5 (Fri) | States do not wrap, requiring user to scroll horizontally even when plenty of space below. Adding a space inbetween each state will solve this (PA, VA, NY, DC) (Scott, assigned to you for design recommendation. If this is a data issue, coordinate with Paul and Jonathan.)
108 | Feature |  | Resolved | Normal | Catch-up on unit tests | Matt Travers | 2015-06-27 15:14 | 0.5 (Fri)
96 | Bug |  | Resolved | Normal | Saved search: No response upon pressing "ok". | Matt Travers | 2015-06-26 13:28 | 0.5 (Fri) | No response upon pressing "ok". Multiple js errors primarily dealing with date. (From Aaron)
115 | Bug | Bug #114: UI: State filters not returned when a saved search is open | Resolved | Urgent | Endpoint: Return states on saved searches | Jonathan Pund | 2015-06-28 17:13 | 0.6 (Mon) | I saved a search and sent the link to myself. (Working.) When I open in a new browser, the states are not populating on the map or labels, and the results do not reflect states.
114 | Bug |  | Resolved | Urgent | UI: State filters not returned when a saved search is open | Jonathan Pund | 2015-06-28 17:13 | 0.6 (Mon) | I saved a search and sent the link to myself. (Working.) When I open in a new browser, the states are not populating on the map or labels, and the results do not reflect states.
121 | Feature |  | Resolved | Urgent | Text update: Should we clear up the distinction between recalls and enforcement events/reports? | Scott McCaughey | 2015-06-28 22:40 | 0.6 (Mon) | Reading over open.fda.gov, I'm noticing that they tend to use the word recall more. Let's just get rid of "Enforcement Events". We're pretty consistent in using recalls, so let's just change the title: Old: "U.S. Food and Drug Administration Enforcement Events" to New: "U.S. Food and Drug Administration Recalls"
127 | Bug |  | Resolved | High | Saved search returns filter criteria, but table does not update with these criteria | Matt Travers | 2015-06-30 15:45 | 0.6 (Mon) | Upon visiting saved search link, specified filters populate the fields, but do not apply to the search until an option is changed (i.e. all results are shown at first). Steps to reproduce: 1) Try this saved search: https://shar.es/1qhBVb 2) Note that the filters come back (Food, "salmonella", NM, TX, OK) 3) Note that the table still lists 17,000 results, which is the full result set. 4) De-select/select one of the states, and the table updats.
83 | Feature | Feature #81: UI, Multi-select: Keep selected state(s) highlighted | Resolved | High | Multi-select: Show names of states selected | Scott McCaughey | 2015-06-29 14:45 | 0.6 (Mon) | As a user, in addition to highlighting the states, I want to see a list of those states selecting for my filter and be able to de-select them individually by clicking on their names, so that I can adjust criteria via form elements in addition to the map. (Newegg search is an example of this.)
119 | Bug |  | Resolved | Normal | If you click a state, then clear, then hover over states they are highlighted | Matt Travers | 2015-06-27 16:12 | 0.6 (Mon) | Steps to reproduce: 1) Click a state (or a few) 2) Clear filters 3) Hover (but don't click) and the states act as if they are highlighted. Notably, they do not populate in the list or change the filter criteria for the table.
113 | Bug |  | Resolved | Normal | IE11: Three date issues. 1) No date picker visible 2) Sorting and filtering by date don't work. | Matt Travers | 2015-06-29 16:52 | 0.6 (Mon) | 1) Date picker doesn't show at all in IE11. 2) Entering text in date fields doesn't apply the filters. 3) Sorting on dates doesn't actually change the order after the first sort.
116 | Bug |  | Resolved | Normal | Remove sort option for States | Matt Travers | 2015-06-27 16:21 | 0.6 (Mon) | States is an array, remove the sort option because it doesn't work.
100 | Bug |  | Resolved | Normal | IE11: Formatting differences | Matt Travers | 2015-07-03 15:10 | 0.6 (Mon) | The style in IE11 is very different than Chrome. You can see that the checkboxes are plain in IE11. While not critical if it's similar functionally, this makes me worry that some other Javascript or style issues are under the hood.
120 | Bug |  | Resolved | Normal | Sticky highlighting: If you click a large number of states (~30), they suddenly clear all filters and highlights | Matt Travers | 2015-06-29 09:32 | 0.6 (Mon) | Clicking every state from the West Coast and going east, eventually all my states and filters reset--the app should allow me (if I want to) to select every state.
111 | Feature |  | Resolved | Normal | Use volume mount for source code in Docker | Robert Buccigrossi | 2015-07-05 19:39 | 0.6 (Mon) | From Johnathan: How about using a mapped volume so that /gsac in the container actually points to your local checked out copy of the source? That way if someone were using this for development, they wouldn't have to rebuild the image every time to incorporate their source code changes. The command "node index.js" would also have to change to "gulp start" so that the filesystem is monitored for changes and node restarted.
112 | Feature |  | Resolved | Normal | Install DB update Cron Job and Documentation | Robert Buccigrossi | 2015-07-05 19:39 | 0.6 (Mon) | Once Paul gets it to you, install and test the DB update from job.
73 | Feature |  | Resolved | Normal | Implement Nagios (local and external) for monitoring | Robert Buccigrossi | 2015-07-05 19:39 | 0.6 (Mon) | Tasks: 1) Implement Nagios on the integration site to monitor Production. 2) Implement Nagios on Production to monitor itself.
105 | Bug |  | Resolved | Normal | Small states: Need ability to select small states | Scott McCaughey | 2015-06-29 14:45 | 0.6 (Mon) | DC is literally one pixel. Users should be able to select the small states in some way (e.g. Allow zooming on the map, provide a multi-select state dropdown that links with map, allow names to be clickable) Scott: Assigned to you for design recommendation. We can coordinate with Matt on right implementation once you've analyzed.
117 | Bug |  | Resolved | Low | Within States column, list of states is not necessarily in ASC order | Jonathan Pund | 2015-07-05 19:36 | 0.6 (Mon)
124 | Support |  | Resolved | High | Operations: Coordinate and test out docker deployment process | Jonathan Pund | 2015-07-01 14:24 | 0.7 (Tue)
130 | Bug |  | Resolved | High | Share buttons not showing after Save | Matt Travers | 2015-06-30 11:49 | 0.7 (Tue)
79 | Feature |  | Resolved | High | Implement and document Production deployment process | Robert Buccigrossi | 2015-07-01 14:56 | 0.7 (Tue)
135 | Feature |  | Resolved | Normal | Add header for TCG info at bottom | Jonathan Pund | 2015-06-30 16:14 | 0.7 (Tue) | Similar to calc.gsa.gov
129 | Bug |  | Resolved | Normal | Full details: Spinner when populating data | Matt Travers | 2015-06-30 14:15 | 0.7 (Tue) | FEEDBACK: Full details pop-up needs visual feedback (e.g. spinner) when waiting for the data to return, because it looks like it?s not working otherwise. Task: Start spinner at click of row, end it at callback once data is received.
134 | Bug |  | Resolved | Normal | Recall Initiation Date: Human readable date | Matt Travers | 2015-06-30 12:23 | 0.7 (Tue) | This is not human readable and needs to be updated: Recall Initiation Date (Report Date) 20120524 (20120822)
128 | Bug |  | Resolved | Normal | Apache Benchmark: | Robert Buccigrossi | 2015-06-30 17:10 | 0.7 (Tue) | Updated to T2 large.
133 | Feature |  | Resolved | Normal | Mobile: Intro logo and text are too large, and require a lot of scrolling to get passed. | Scott McCaughey | 2015-06-30 23:04 | 0.7 (Tue)
123 | Support |  | Resolved | High | Code Review: Review public folder and angular pieces with code review template | Jonathan Pund | 2015-07-05 19:34 | 0.9 (Thurs)
137 | Bug |  | Resolved | Normal | De-selecting all valid choices for multi-select should return 0 table rows | Jonathan Pund | 2015-07-05 19:37 | 0.9 (Thurs) | If a user either a) de-selects all Types or b) de-selects all severities, there are still entries in the table. Logically, the table should be zero in either case, since all entries have a type and all entries have a severity.
138 | Bug |  | Resolved | Normal | Error handling for date ranges | Matt Travers | 2015-07-05 19:37 | 0.9 (Thurs) | If a user enters crazy date ranges (e.g. 12/01/0001 to 12/01/3000), the user gets a javascript console error that's kind of ugly. In this case, aren't the dates technically valid and we should just return everything? If not, we should put in a more elegant validation that only allows certain dates.
136 | Support |  | Resolved | Normal | Code review: Back end | Matt Travers | 2015-07-05 19:37 | 0.9 (Thurs)
131 | Feature |  | Resolved | Normal | Save and Share is not very intuitive: Show share buttons and add directions for Save then Search. | Scott McCaughey | 2015-07-05 19:34 | 0.9 (Thurs) | FEEDBACK: Not very intuitive to know to save the search before sharing?I don?t know that I *can* share (i.e. because Share is hidden) until I save. Either 1) keep share option visible and leave it greyed out until it?s been saved, or 2) have ?Share? save and then share as one click. Task: 1) Scott to investigate alternatives that don't involve re-factoring search.
118 | Bug |  | Resolved | Low | If all 51 states + DC is returned, show "Nationwide" in States column | Jonathan Pund | 2015-07-05 19:35 | 0.9 (Thurs)
143 | Feature |  | Resolved | Low | Help icon text for product type is very long and difficult to view |  | 2015-07-05 19:36 | 0.9 (Thurs) | Info text for product type is very long and is difficult to view on screen. No abilty to scroll down and box disappears when the '?' button loses focus. Either make box wider and/or provide ability to scroll within box.
147 | Bug |  | Resolved | Low | On page load: Variable names for the search name and description appear briefly |  | 2015-07-05 19:35 | 0.9 (Thurs) | Upon page load, the variable names for the search name and description appear briefly. This may have relation to page load speed. https://drive.google.com/open?id=0B4WX-rJogAj0NW1Ld2hIWG9NdlU
152 | Bug |  | In Progress | High | Re-run data normalization from api.fda.gov (WAS: Product descriptions are truncated in the UI) | Robert Buccigrossi | 2015-07-06 12:17 | 1.0 (Monday) | Original question: If a user types in Peanut for product description, everything is food and appears peanut related except for one random device, Firm = Customed Inc and Product Description = Open Heart Tray. I can't find the word peanut in there anywhere...so why is it showing up? From Butch: The description is truncated (so if there's a bug, it's in the display, not the search). The full description is (PEANUT in bold below): OPEN HEART TRAY - - PACK A .....
153 | Feature |  | Resolved | Normal | API: Implement two API service calls, one for full normalization and one per event | Jonathan Pund | 2015-07-06 12:17 | 1.0 (Monday) | One of the US Digital Services playbook mapping items is this: "Provide datasets to the public, in their entirety, through bulk downloads and APIs (application programming interfaces)" Do we have an easy way of exporting the current search results as a CSV for download?
155 | Feature | Feature #153: API: Implement two API service calls, one for full normalization and one per event | Resolved | Normal | Endpoint: Return parsed states for a given event id | Jonathan Pund | 2015-07-06 12:03 | 1.0 (Monday) | Return distribution states of the product when given a noun and event id
156 | Feature | Feature #153: API: Implement two API service calls, one for full normalization and one per event | Resolved | Normal | Endpoint: Return parsed states for all recalls in a given noun (i.e. recall type) | Jonathan Pund | 2015-07-06 12:15 | 1.0 (Monday) | Return the distribution states of a product for all recalls in a given noun
139 | Feature |  | Resolved | Normal | Optimize data base queries and re-run load tests to confirm impact | Robert Buccigrossi | 2015-07-05 22:23 | 1.0 (Monday)
69 | Feature |  | Resolved | Normal | Update Google analytics for tracking actual page interactions | Scott McCaughey | 2015-07-05 19:34 | 1.0 (Monday)
74 | Feature |  | Resolved | Normal | Create a design style guide or pattern library | Scott McCaughey | 2015-07-05 19:35 | 1.0 (Monday)
110 | Support |  | New | High | Final Production Promotion Process | Robert Buccigrossi | 2015-06-26 13:08 |  | For final production roll-out we need to: * Make sure that production's system is upgraded to t2.large for usability * Merge develop to master * Merge develop to GitHub * Dump database and gzip it to gsac/docker/gsac.sql.gz from integration * Promote database to production * Turn off Jenkins in production * Final promotion of source code to production * Acceptance test production environment
132 | Feature |  | New | High | Save and search: Not very intuitive, consider refactoring URLs to allow for one-step sharing |  | 2015-06-30 09:48 |  | FEEDBACK: Not very intuitive to know to save the search before sharing?I don?t know that I *can* share (i.e. because Share is hidden) until I save. Either 1) keep share option visible and leave it greyed out until it?s been saved, or 1) have ?Share? save and then share. Task: Would need to refactor URLs to keep search criteria for one-step save/share.
140 | Bug |  | New | Normal | Need to resolve tension between state highlighting versus heat map colors |  | 2015-07-03 15:11 |  | From Paul Malone and confirmed by focus group. General issue is that state highlighting obscures heat map, and should be made more consistent. From Paul: "The clicking of the map confuses me. I think if we allow users to click the map and color a state red, then the rest of the shading should go away completely. Effectively setting the filter on state. IF they untoggle all the Reds, then shading returns ." From focus group: Clicking states obscures the heat map color of the selected states. It would be better to have a less invasive highlight, like darkening the borders or setting the other state out of focus, as the heat map indicator is still a useful piece of information."
144 | Feature |  | New | Normal | Add Severity (and other columns) missing from table |  | 2015-07-03 15:10 |  | include severity in table. OR perhaps allow user to select columns to display
141 | Bug |  | New | Normal | With certain distribution, heat map color distribution seems non-ideal |  | 2015-07-03 15:29 |  | From focus group: Need to revisit the distribution of the map shading: If there isn't a large range of values in a search (filter 5/24/2012 to 6/24/2012), a state appears white with 180 results whereas a dark blue state only has 251. At quick glance user may think the white states have 0 results, but really they are not far from the dark blue. Also if there is a perfect distribution across states (search 5/24/2012 to 5/24/2012), the entire map appears white.
149 | Bug |  | New | Normal | Individual clear filter only appears in IE |  | 2015-07-03 14:52 |  | From usability testing: To clear a text search filter, an "X" only appears to the right in IE11 (except for date fiters, which appears only Chrome, mobile provides different function for clearing date)
150 | Feature |  | New | Normal | Recalls press release page should open in new tab/window |  | 2015-07-03 15:09 |  | Have link to recalls press release page open in new tab/window.
142 | Feature |  | New | Low | Recalling firm autocomplete: Can get too long and should be cleaned up |  | 2015-07-03 14:33 |  | Search results auto complete list for Recallng Firm can get very long. Would look cleaner if provided the ability to scroll withing the results (instead of on the page itself). Example: search "inc" in realling firm.
64 | Feature |  | New | Low | Allow users to change their color palette for the color bands |  | 2015-06-22 12:00
151 | Feature |  | New | Low | Mobile UI: Indicate table results page |  | 2015-07-03 15:01 |  | Mobile: No indication what page number you are on, just First, Prev, Next, Last. Would be helpful to have page number.
145 | Feature |  | New | Low | Re-sizing window can lead to "stacked" view |  | 2015-07-03 14:40 |  | From usability testing: Consider lowering the min window width requirement for "standard" view on desktops. On both of my screens, the browser window must be about 2/3 to 3/4 the width of my screen for the standard view, else it reverts to the "stacked" view. The standard view is much more user friendly, but I worry that it is not uncommon for users to have smaller browser windows. There is currently a good amount of white space on the sides of the map (above the scale), we may be able to gain space there.
148 | Bug |  | New | Low | On mobile, some state names are misaligned, but still usable |  | 2015-07-03 14:50 |  | On mobile (Android Chrome), some state names are misaligned (see screenshot for example) https://drive.google.com/open?id=0B4WX-rJogAj0TDh3ajQ5WlhHRmtqNFFFZWNKZ3JqakphV0pV&authuser=1
146 | Feature |  | New | Low | Display total results higher on page |  | 2015-07-03 14:42 |  | From usability testing: When there are zero results, it is not immediately clear that this is the case. Must scroll down to see "Showing 0 to 0 of 0 entries". Would be nice if the total number of results was visible when setting the filters. There's a general need for this as well.
89 | Feature | Feature #88: UI, autocomplete: Turn off autocomplete on Reason for Recall and Product Description | New | Low | UI, autocomplete: Use postgres weighted text search to provide better results for Reason for Recall and Product Description |  | 2015-06-24 12:28 |  | Users complained that the autocomplete for Reason for Recall and Product Description were bit useful because of how long (and specific) these fields were.
62 | Feature |  | New | Low | Preview related news stories based on keyword matches for a particular enforcement event |  | 2015-06-22 11:53 |  | As a user, when I'm reviewing the details of an event, I would like to see related news stories to see if the recall is being talked about in the news.
109 | Feature |  | New | Low | Provide list of unmatched/unnormalized data for reference to users |  | 2015-06-29 12:21