## Test Cases
Test Case | Chrome | IE11 | Mobile | Notes | Last Completed | Disposition
Select state from map | Pass | Pass | Moderate Pass | Mobile: Some state names are misaligned. | 2015-07-02 14:45 | Mobile issue: Accepted as-is, Ticket #148
Filter by product type | Pass | Pass | Pass | IE11: Checkbox styling does not apply in IE | 2015-06-29 21:11
Filter by date range included in data (1/01/2012 - 12/31/2012) | Pass | Pass | Pass | Mobile: Previous date picker had better mobile ui (but this one is still ok). | 2015-06-29 21:30
Filter by date range excluded by data (4/01/1980 - 4/01/1985) | Pass | Pass | Pass |  | 2015-06-29 21:30
Clear date range search | Pass | Pass | Pass | No longer have option to clear other than to press backspace (not a big deal). Option is only there in IE | 2015-06-29 21:30
Remove specific state | Pass | Pass | Pass |  | 2015-06-29 22:13
Filter on product description ("software", "seasoning", "Sulfamethoxazole", "asdfds" | Pass | Pass | Pass |  | 2015-06-29 22:30
Filter on reason for recall ("peanut", "Salmonella", "asfd" | Pass | Pass | Pass |  | 2015-06-29 23:00
Filter on recalling firm ("Trophy Nut Co", " us end ", "inc", "fdsf" | Pass | Pass | Pass |  | 2015-06-29 23:00
Filter on severity | Pass | Pass | Pass |  | 2015-06-29 23:00
Combinatio of filters (All types, 4/7/2009-4/8/2009, "nut", "salmonella", "trophy nut co", Class I | Pass | Pass | Pass |  | 2015-06-29 23:00
Save search | Pass | Pass | Pass | Upon clicking the saved link, the filter fields were correct but they did not apply to the search. | 2015-06-29 23:50
Press cancel when saving search | Pass | Pass | Pass |  | 2015-06-29 23:50
Email to friend (aaron.pollon@tcg.com) | Pass | Pass | Pass |  | 2015-06-29 23:50
View emailed search | Pass | Pass | Pass | No way for "friend" re-save a revised search. | 2015-06-29 23:50
Change number of entries shown | Pass | Pass | Pass |  | 2015-06-29 23:50
Sort by each column | Pass | Pass | Pass |  | 2015-06-29 23:50
Browse through search result pages, jump to specific page | Pass | Pass | Moderate Pass | Mobile: No indication what page number you are on. | 2015-06-29 23:50 | Accepted as-is, Ticket #151
View field description | Pass | Pass | Pass | All: Difficult to view long text (see additional bug) | 2015-07-02 14:43
Clear out individual filter via "X" | Fail | Pass | Fail | An "X" only appears to the right in IE11 (except for date fiters, which appears only Chrome, mobile provides different function for clearing date) | 2015-06-29 23:50 | Accepted as-is, Ticket #149
Clear all filters | Pass | Pass | Pass |  | 2015-06-29 23:50

## Additional BugsFeedback
Issue Type | Component | Description | Priority | Reported | Reported By | Status | Last Checked | Screenshot | Disposition
Bug | Share | Share only works when the search is first saved. Otherwise the link does not display the sent search. It should not be necessar to save a search in order to send, but if so, either disable the share links until the search is saved or prompt the user to save upon clicking share | 4 - Critical | 2015-06-24 23:49 | Aaron | Resolved | 2015-06-30 01:20
Bug | Results | Results are limitied to 100 (seems to retrieve first 100 results, oldest first). Sorting by column only sorts on the 100 returned results, not the actual result set that matches the criteria. Does not give a user a correct sense of the results, particularly when it comes to date since the more recent results would be missing. | 4 - Critical | 2015-06-24 10:00 | Aaron | Resolved | 2015-06-28 00:19
Bug | Saved Search | Selected states are not included in saved search | 4 - Critical | 2015-06-28 00:44 | Aaron | Resolved | 2015-06-30 01:30
Bug | Start/End Date (IE11) | No date picker visible, unable to sort by date | 4 - Critical | 2015-06-25 00:05 | Aaron | Resolved | 2015-06-30 01:30
Improvement | States Column | States do not wrap, requiring user to scroll horizontally even when plenty of space be1 - Low. Adding a space inbetween each state will solve this (PA, VA, NY, DC) | 3 - High | 2015-06-24 22:19 | Aaron | Resolved | 2015-06-30 01:14
Bug | Map | For small states, need ability to click on state name to select. (Ex. Not possible to click on DC) | 3 - High | 2015-06-24 23:31 | Aaron | Resolved | 2015-06-30 01:14
Improvement | Map | When there are zero results, the map completely disappears (all states turn white). States are still selectable (which is fine) Map should keep the state outline to still remain visible. | 3 - High | 2015-06-24 10:00 | Aaron | Resolved | 2015-06-30 01:20
Bug | "Email" Option | Email preview and body is expecting variables savedSearch.name and savedSearch.description (probably want to remove) | 3 - High | 2015-06-24 10:00 | Aaron | Resolved | 2015-06-25 00:31
Improvement | Map/Search | No method of viewing results for entire country | 3 - High | 2015-06-24 10:00 | Aaron | Resolved | 2015-06-28 00:18
Bug | Saved Search | Upon visiting saved search link, specified filters poopulate the fields, but do not apply to the search until an option is changed (i.e. all results are shown at first). | 3 - High | 2015-06-28 00:44 | Aaron | Resolved | 2015-06-30 05:39
Improvement | Share | Revised functionality of requiring a search to be saved before showing share options is not intuitive. If requirement is kept, consider keeping the share options visible, but with a tool tip prompting the user to save first. If clicked on, a messege should inform the user that a save is required first. Ideal functionality is that a search can be shared without saving (or at least having the user perform the save) | 3 - High | 2015-06-28 00:56 | Aaron | Resolved | 2015-06-30 01:30
Bug | UI | table duplicating records: pick 2015 date range pick reason = 'fatal' pick firm = "Henry" 1 record in DB 2 records in v_state_enforcements (see to right) should appear as one record with two states in table but shows as two records | 3 - High | 2015-06-25 | malone | Resolved
Bug | UI | reorder state abbvs alpha ASC, it's DESC now | 3 - High | 2015-06-25 | malone | Resolved
Bug | UI | reset form F5 enter start date 5/1/2015 click food, click severity, click texas. From this point, changing search settings has no effect | 3 - High | 2015-06-25 | malone | Resolved | 2015-06-30 01:50
Improvement | UI | The clicking of the map confuses me. I think if we allow users to click the map and color a state red, then the rest of the shading should go away completely. Effectively setting the filter on state. IF they untoggle all the Reds, then shading returns and perahps we could have a "Total Recalls = xx" s appear to show the sum of states selected | 3 - High | 2015-06-25 | malone | Open |  |  | Accepted as-is, Ticket #140
Bug | UI | The default screen shows all recalls, but the dates defult to not entered. If we default to all dates, use: end date = today's date start date = 1/1/2012 | 3 - High | 2015-06-25 | malone | Won't Fix |  |  | Won't fix
Bug | Map | Map is sometimes cutoff upon page load. Haven't been able to determine the cause | 3 - High | 2015-06-28 18:10 | Aaron | Resolved | 2015-07-02 14:28 | https://drive.google.com/open?id=0B4WX-rJogAj0YTlTQmljT3ZHRU0&authuser=1
Improvement | Map | Need to revisit the distribution of the map shading: If there isn't a large range of values in a search (filter 5/24/2012 to 6/24/2012), a state appears white with 180 results whereas a dark blue state only has 251. At quick glance user may think the white states have 0 results, but really they are not far from the dark blue. Also if there is a perfect distribution across states (search 5/24/2012 to 5/24/2012), the entire map appears black (maybe just need to change the darkest color to fix that). | 3 - High | 2015-06-28 18:23 | Aaron | Open | 2015-07-02 17:42 | https://drive.google.com/open?id=0B4WX-rJogAj0X0MtQlBXQ0h1b0k&authuser=1 | Accepted as-is, Ticket #141
Bug | Date Picker | (Needs verified) Occasional error in date picker, haven't quite figured out the exact circumstance. Seems related to typing in a date (instead of using picker). Will update when confirmed | 3 - High | 2015-06-28 22:08 | Aaron | Needs Verified |  |  | Can't reproduce
Improvement | Returning to and editing a saved search | 1. The "your search has been saved" text remains visible for anyone who visits the search. So if I send the link to someone else, they would see the text that their search has been saved, even though they were not the one who saved it. 2. Since the save button now disappears, a person who receives a saved search can make adjustments to the filters, but has no way of saving it themselves. Maybe we're ok with that for now? I cool fix would be auto detect for changes and show the save button. This would also prevent someone from clicking share on a revised search, which would actually share the original search. Show less | 3 - High |  | Aaron | Resolved | 2015-07-02 17:39
Bug | Share Options | Hovering over the "Email" share or green "Share" button (rightmost) cause them to open. This is unexpected as a click should be required | 2 - Medium | 2015-06-24 22:13 | Aaron | Resolved | 2015-06-30 01:14
Bug | Filed Description (Mobile) | Mobile: Unable to click to view the field description without also selecting the field | 2 - Medium | 2015-06-24 23:38 | Aaron | Resolved | 2015-07-02 14:28
Improvement | "Email" Option | May want to change the subject of the email from "GSA Challenge" to "FDA Recall" | 2 - Medium | 2015-06-24 10:00 | Aaron | Resolved | 2015-06-25 00:31
Bug | Table Row | Unable to select text in table to copy/paste. Row collapses when attempted (tested in Chrome and IE11) | 2 - Medium | 2015-06-24 10:00 | Aaron | No Longer an Issue | 2015-06-30 01:20
Improvement | Text Search Options | Search results auto complete list for Recallng Firm can get very long. Would look cleaner if provided the ability to scroll withing the results (instead of on the page itself). Example: search "inc" in realling firm. | 2 - Medium | 2015-06-24 10:00 | Aaron | Open | 2015-07-02 17:43 |  | Accepted as-is, Ticket #142
Improvement | Product Type Info Text | Info text for product type is very long and is difficult to view on screen. No abilty to scroll down and box disappears when the '?' button loses focus. Either make box wider and/or provide ability to scroll within box. | 2 - Medium | 2015-06-24 10:00 | Aaron | Open | 2015-07-02 14:28 |  | Accepted as-is, Ticket #143
Improvement | Recalling Firm | Need ability to submit entered text without selecting an autofill suggestion and without reselecting a state. Pressing enter will select the currently highlighted sugestion. | 2 - Medium | 2015-06-25 00:38 | Aaron | Resolved | 2015-06-28 00:44
Bug | Product Type | Deselecting all product types shows zero results on map, but (all?) results in the table. For consistency, would expect the table to be empty (no results) | 2 - Medium | 2015-06-25 16:37 | Aaron | No Longer an Issue | 2015-06-30 01:30
For Discussion | Mobile UI | Should map appear first when viewing on mobile/small screen? | 2 - Medium | 2015-06-28 17:07 | Aaron | Resolved | 2015-06-30 01:30
Improvement | UI | include severity in table. OR perhaps allow user to select columns to display | 2 - Medium | 2015-06-25 | malone | Open |  |  | Accepted as-is, Ticket #144
Improvement | UI | table rendering of csv state abbreviations., recommend list them vertically. just replace , with \n | 2 - Medium | 2015-06-25 | malone | Resolved | 2015-06-30 01:50
Improvement | UI | add favicon | 2 - Medium | 2015-06-25 | malone | Resolved
Improvement | Recall Details | Add ability to close recall details from top of window. User must scroll to bottom. Particularly important for mobile. | 2 - Medium | 2015-06-28 14:52 | Aaron | Resolved | 2015-06-30 01:50
Bug | Recall Type | Error occurs when no recall type is selected (previosuly would display zero results as expected) | 2 - Medium | 2015-06-28 21:11 | Aaron | Resolved | 2015-07-02 17:42 | https://drive.google.com/open?id=0B4WX-rJogAj0WnFLM250ei1hVWs&authuser=1
Improvement | UI Sizing | Look into lowering the min window width requirement for "standard" view on desktops. On both of my screens, the browser window must be about 2/3 to 3/4 the width of my screen for the standard view, else it reverts to the "stacked" view. The standard view is much more user friendly, but I worry that it is not uncommon for users to have smaller browser windows. There is currently a good amount of white space on the sides of the map (above the scale), we may be able to gain space there. | 2 - Medium | 2015-06-28 21:25 | Aaron | Open
Improvement | Search Result Count | When there are zero results, it is not immedialtley clear that this is the case. Must scroll down to see "Showing 0 to 0 of 0 entries". Would be nice if the total number of results was visible when setting the filters. | 2 - Medium | 2015-06-24 10:00 | Aaron | Open | 2015-07-02 17:55 |  | Accepted as-is, Ticket #146
Improvement | Saving Search | Should provide feedback to user that search was saved. Currently user would have to notice the url change. | 2 - Medium | 2015-06-28 23:13 | Aaron | Resolved | 2015-07-02 14:28
Bug | Title/Description | Upon page load, the variable names for the search name and description appear briefly. | 3 - High | 2015-06-30 10:44 | Aaron | Resolved | 2015-07-03 23:59 | https://drive.google.com/open?id=0B4WX-rJogAj0NW1Ld2hIWG9NdlU | Accepted as-is, #147
Improvement | Errors | If an error keep ocurring in the search (such as invalid year in date range), the errors will keep piling on until user x's each one out. | 1 - Low | 2015-06-24 21:59 | Aaron | No Longer an Issue | 2015-06-30 01:14
Bug | Map (Mobile) | On mobile (Android Chrome), some state names are misaligned (see screenshot for example) | 1 - Low | 2015-06-24 23:31 | Aaron | Open | 2015-07-02 17:39 | https://drive.google.com/open?id=0B4WX-rJogAj0TDh3ajQ5WlhHRmtqNFFFZWNKZ3JqakphV0pV&authuser=1 | Accepted as-is, #148
Improvement | "Email" Option | If the email option is used, we rely on the user to add context to the link/website. In body of email, maybe add a brief sentence for context such as "Sent via FDA Recall events app". Also consider adding a link to the site (in addition to search specific). | 1 - Low | 2015-06-24 10:00 | Aaron | Resolved | 2015-06-25 00:31
Question | Share Options | Are we able to select which share options are visible? "LinkedIn" may not be necessery for this app, Pinterest may not be either. | 1 - Low | 2015-06-24 10:00 | Aaron | Resolved | 2015-06-25 00:31
Improvement | All Text Filters | Is there in Chrome, requires hitting space. | 1 - Low | 2015-06-24 10:00 | Aaron | Not an Issue | 2015-06-28 00:18
Bug | Severity Filter / Type filter | When no options are selected for severity, all results are displayed. This is inconsistent with the "Recall Type" filter. Either showing all or none is fine, but should be consistent. | 1 - Low | 2015-06-24 10:00 | Aaron | Resolved | 2015-07-02 17:56
Bug | Date Range | A data range that produces a js error gives no feedback to the user. Example: 12/01/0001 to 12/01/3000. UPDATE: Looks an error has been added (great!), but it says "There was a system problem while performing the search. Check the console for details." (not so great) I would remove "check console...". Ideally the error would reference the field that caused it so the user can correct. Its ok to have a catch all "There was a problem performing your search", but the user would not check the console. | 2 - Medium | 2015-06-28 00:30 | Aaron | Resolved | 2015-07-03 15:21 |  | Confirm fix
Bug | Text Filters | To clear a text search filter, an "X" only appears to the right in IE11 (except for date fiters, which appears only Chrome, mobile provides different function for clearing date) | 1 - Low | 2015-06-25 00:11 | Aaron | Open | 2015-07-02 17:39 |  | Accepted as-is, Ticket #149
Improvement | Saved Search | Once a search is saved, the title and description are listed at top, but without labels. | 1 - Low | 2015-06-25 00:16 | Aaron | Resolved | 2015-06-30 01:30
Improvement | Link to Recalls Press Releases | Have link to recalls press release page open in new tab/window. | 1 - Low | 2015-06-25 00:19 | Aaron | Open | 2015-07-02 17:39 |  | Accepted as-is, Ticket #150
Improvement | Mobile UI | When smart phone is rotated for a wider screen, table columns remain same width. Would be a good opportunity to display additional columns (states, type) or to expand current columns | 1 - Low | 2015-06-28 17:52 | Aaron | Resolved | 2015-06-30 01:30
Bug | Details pop-up | Details pop-up appears to be truncating the fields prematurely. For instance, searching for "peanut" in the description field leads to a result with a device from Customed Inc. In the pop-up, the word peanut never appears, but it is actually in the source data. | 3 - High | 2015-07-03 16:19 | Aaron/Butch/Alex | Resolved | 2015-07-03 16:19 |  | Ticket #152